## Mind Maps
Prepared By: Md. Asif Hassan

## TestScenarios
Project Name | Startech.bd.com
Reference Document | -
Created By | Md. Asif Hassan
Creation Date | 2025-02-02
Approval Date | 2025-07-02
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Register Account" functionality | P1 | 30
TS_004 |  | Validate the working of the "Login" functionality. | P0 | 35
TS_006 |  | Validate the working of "Add to cart" functionality. | P1 | 5
TS_006 |  | Validate the working of " Total amount" functionality. | P1 | 1
TS_009 |  | Validate the working of "Screenshot" functionality. | P4 | 1
TS_010 |  | Validate the working of "Search Bar" functionality. | P4 | 1
TS_012 |  | Validate the working of "Gadget Fest" functionality. | P5 | 1
TS_013 |  | Validate the working of "Get offer" functionality. | P5 | 5
TS_014 |  | Validate the working of "OTP" functionality. | P1 | 5
TS_015 |  | Validate the working of "Forgotten Password?" functionality. | P2 | 10
TS_016 |  | Validate the working of "Mobile Deal" functionality. | P3 | 1
TS_017 |  | Validate the working of "PC Builder" functionality. | P3 | 1
TS_018 |  | Validate the working of "accessories"functionality. | P4 | 1
TS_019 |  | Validate the working of "office-equipment" functionality. | P5 | 1
TS_020 |  | Validate the working of "SUPPORT"functionality. | P5 | 1
TS_021 |  | Validating the ability to take user to their designated floor | P1 | 4

## TestCase
Product Name |  | Startech | TC Start Date | 28/09/2024 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 2024-02-10 | TC Execution End Date | - - |  |  |  |  | PASS | 58
Epic |  |  | Test Case Developed By | Md. Asif Hassan | Browser (tested) | Yes |  |  |  |  | FAIL | 9
Developer Name (TL) |  |  | Test Case Reviewed By | - | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 67
| Module | Type of Testing | Features | Test Cases | Exepected Result | #SL | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search 'Startech' 3. Go to the website. |  |  | Passed
2 |  |  | Login | Verify the alignment of displayed elements on the login screen should be compatible in cross browsers testing. | Should be clicked on the "Login" link. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link |  |  | Failed
3 |  |  |  | Verify all login-related elements and fields are present on the login page. | Should be present the mandatory field . | Found as per expectation. | None | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the spelling and grammatical mistakes. |  |  | Failed
4 |  |  |  | Verify the displayed element are in alignment from. | Elements should be in aligment from. . | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check * this sign.
5 |  |  |  | Verify that the size, color, and UI of different elements should match the specifications. | Should be as per the client requirement | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check * this sign.
6 |  |  |  | Verify that the login page of the application is responsive and aligns properly on different screen resolutions and devices | A text should appear over the fields. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check Hover over every fields. |  |  | Passed
7 |  |  |  | Verify login page title. | The title should be as client requirement | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the alignment. |  |  | Passed
8 |  |  |  | Verify the cursour in the "Email box " by default. | Fields should be in empty position. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the input fields. |  |  | Passed
9 |  |  |  | Verify the " Confirm" button hovering or not. | when hovering the button should be changed the color. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
10 |  |  |  | Verify that there is a checkbox with the label "remember password" on the login page. | There should be a check box for this action. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
11 |  |  |  | Verify the user credential remained on the field after clicking remember and get back to the login screen again. | user credential should be reminder | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
12 |  |  |  | Verify that the user will be able to log in with their account with the correct credential | User should be able to login with correct credintial | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
13 |  |  |  | Verify that the user can access all controls and elements by pressing the Tab key from the keyboard. | Should be able to use Tab key | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
14 |  |  |  | Verify that the password entered should be in encrypted form. | The password entered should be in encrypted form. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
15 |  |  |  | Verify whether an eye icon is added to the password field or not. | Should be there a eye icon | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
16 |  |  |  | There should be an email verification check, as the user verifies the email address then the user is able to view the dashboard and access features. | Should be an email verification check | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
17 |  |  |  | Verify the error message should display after just entering an email address and leaving the password field blank. | Should give an error message | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
18 |  |  |  | Verify the error message should display after just entering a password and leaving the email field blank. | The error message should display after just entering a password | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
19 |  |  |  | Verify the error message should display after entering the invalid credentials. | The error message should display after just entering a password | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
20 |  |  |  | Verify the error message should display after entering an invalid email format. | The error message should display if the email is invalid | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
21 |  |  |  | Verify the displayed error message grammar should be correct. | Erro massage should be grammaticaly correct | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
22 |  |  |  | Verify the displayed error message spell should be correct. | The spelling of error message should be correct. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
23 |  |  |  | Check logged in user should not log out on closing the browser. | Browser should not be closed when new browser is opend | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
24 |  |  |  | Verify logged-in user doesn’t log out by clicking the back button on the browsers tab. | User should not out logged out by clicking the back button | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
25 |  |  |  | Verify all the functionalities should be working condition as the user sign-in from social login in Facebook and Google. | Should be logged in the current page if the user use the social media . | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
26 |  |  |  | Verify logged-in user copies the URL and pastes it into a new browser window, it should redirect to the login page | User should copy the url. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
27 |  |  |  | Verify it should not be always in loading in case the user adds an invalid email and password. | User should not not be always in loading in case the user adds an invalid email and password. | Found as per expectation. | None | 1. Goto the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the " Confirm" button. |  |  | Passed
28 |  |  |  | Keeping mandatory fields blank | Should be blanked to put data. | Found as per expectation. | None | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and check the fields. |  |  | Passed
29 |  |  |  | Checking firstname and lastname field is case insensitive | Should accept the provided input | Found as per expectation. | AAcccEEE | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
30 |  |  |  | Entering blank at first position in firstname and lastname field. | Should not accept the provided input | Found as per expectation. | AAcccEEE & BBcceE | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
31 |  |  |  | Inputting first name and last name with special characters. | Should not accept this special character as provided input. | Found not as per expectation. | *($# *($# | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. | Special character error |  | Failed
32 |  |  |  | Inputting firstname and lastname with numbers | Should not accept a number as provided input. | Found not as per expectation. | 12345 & 67890 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. | Numer errors in first and last name |  | Failed
33 |  |  |  | Inputing firstname and lastname with decimal numbers | Should not accept a any decimal number as provided input. | Found not as per expectation. | .arAS & ,GSdf | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. | Decimal value error |  | Failed
34 |  |  |  | Inputing firstname and lastname with alphanumeric characters | Should accept the provided input | Found as per expectation | John88 lizz44 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
35 |  |  | Register Account | Inputing firstname and lastname with alphabets | Should accept the provided input | Found as per expectation | John Austin | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
36 |  |  | Register Account | Entering comma between alphabets for firstname and lastname | Should not accept comma between the first name and last name | Found not as per expectation | Firstname: Joh,n Lastname: Aus,tin | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. | comma error |  | Failed
37 |  |  |  | Giving space between alphabets for firstname and lastname | Should have a gap between the first name and last name | Found as per expectation | John Austin | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
38 |  |  |  | Checking newsteller checkbox. | Should function successfully. | Found as per expectation | N/A | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
39 |  |  |  | Validating an email id can only be used one time | Should not allow user to register and display a pop message | Found as per expectation | mdasif.hassan@gmail.com | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
40 |  |  |  | Checking by inputing invalid email format | Should not accept the provided input and display an error message | Found not as per expectation. | wecokix691@@@@muzitp.com | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. | Invalid email users also can registration. |  | Failed
41 |  |  |  | Checking by inputing valid email format | Should accept the provided input a. | Found as per expectation | mdasif.hassan@gmail.com | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. |  |  | Passed
42 |  |  |  | Checking by inputting invalid mobile number . | Should not accept the provided input and display an error message | Found as per expectation | 19348389921 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field. | Give error |  | Failed
43 |  |  |  | Check the sending OPT. | Should send an OTP to the valid phone number. | Found as per expectation | 1934838992 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue |  |  | Passed
44 |  |  | Register Account | Check the sending OPT numer | Should send an OTP to the valid phone number with numeric number. | Found as per expectation | 7070 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue |  |  | Passed
45 |  |  |  | Checking password and confirm field values are masked | Should be masked. | Found as per expectation | None | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue |  |  | Passed
46 |  |  |  | Inputing invalid combinations of characters in password and confirm password field | Should not allow user to register and display a pop message | Found as per expectation | john8888 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue |  |  | Passed
47 |  |  |  | Inputting weak password length | Should allow user to register | Found as per expectation | hhg#k88 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
48 |  |  |  | Inputing medium password length | Should allow user to register | Found as per expectation | hhg#k89 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
49 |  |  |  | Inputing strong password length | Should allow user to register | Found as per expectation | hgjkgjkjkjh!&*77 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
50 |  |  |  | Inputing valid data for password and confirm password | Should allow user to register | Found as per expectation | john@8888 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
51 |  |  |  | Checking visiting the site again by unselecting 'Remember Me' | Should allow user to register | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 Remember Me: Unselect | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
52 |  |  |  | Checking captcha inputing invalid data | Should not accept the captcha and pop an error message | Found as per expectation | ghj8 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
53 |  |  |  | Keeping captcha field blank | Should not enable user to register and pop an error message | Found as per expectation | N/A | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
54 |  |  |  | Checking captcha is case insensitive | Should be case insensitive | Found as per expectation | HgWy7 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
55 |  |  |  | Checking new captcha is generated on page reload | Should generate new captcha | Found as per expectation | v5Br | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
56 |  |  |  | Checking new captcha is generated adding wrong captcha | Should generate new captcha | Found as per expectation | k9nb | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
57 |  |  |  | Checking reload captcha option | Should generate new captcha | Found as per expectation | N/A | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
58 |  |  |  | Checking captcha inputing valid data | Should allow user to register | Found as per expectation | m433 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
59 |  |  | Account Login | Check login with valid mail | Should allow user to login | Found as per expectation | password | 1. Go to the URL https://www.startech.com.bd/ . 3. Click on login link. |  |  | Passed
60 |  |  |  | Check login with invalid mail | Should not allow user to login. | Found as per expectation | mdasif.hassan@gmail.com | 1. Go to the URL https://www.startech.com.bd/ . 3. Click on login link. |  |  | Passed
61 |  |  |  | Check login with valid phone number | Should allow user to login | Found as per expectation | hassan124238 | 1. Go to the URL https://www.startech.com.bd/ . 3. Click on login link. |  |  | Passed
62 |  |  | Account Login | Check login with Invalid phone number | Should not allow user to login. | Found as per expectation | hassan124234569 | 1. Go to the URL https://www.startech.com.bd/ . 3. Click on login link. |  |  | Passed
63 |  |  |  | Checking login button with valid credentials | Should allow user to register | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 | 1. Go to the URL https://www.startech.com.bd/ . 3. Click on login link. |  |  | Passed
64 |  |  |  | Checking login button with valid credentials | Should allow user to register | Found as per expectation | Firstname: veronica Lastname: dsouza Email: veronicadsouza970@gmail.com Password: veronica@44 Confirm Password: veronica@44 | 1. Go to the URL https://www.startech.com.bd/ . 3. Click on login link. |  |  | Passed
65 |  |  |  | Checking captcha inputing valid data | Should allow user to register | Found as per expectation | m433 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and password. |  |  | Passed
66 |  |  |  | Checking copy paste functionality in every field | Should copy and paste text from fields | Functioning successfully | jane1111 | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and |  |  | Passed
67 |  |  |  | Checking keyboard tab button functionality | Should switch to another field and highlight text | Functioning successfully | Enter tab in every field | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and |  |  | Passed
68 |  |  |  | Checking keyboard enter button functionality | Should switch to another field | Functioning successfully | input Enter in every field | 1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data in the mentioned field. 4. Go to Continue. 5. give otp and |  |  | Passed
69 |  |  |  | Remember Me' checkbox should be selected according to user | [6 empty] | Failed
70 |  |  | Improvement Scopes | A maximum length of the password should be defined if user put the max value
71 |  |  |  | Place the 'Forgot your password link below the Password field
72 |  |  |  | Social media links may be in include under the login section
73

## Test Summary Report
Test Case Report | [5 empty] | Result
Project Name | Startech bd LTD |  |  |  |  | Total No. | Status
Module Name | Account |  |  |  |  | 58 | PASS
Feature Name | Register Account & Account Login |  |  |  |  | 9 | FAIL
Test Case Version | 1 |  |  |  |  | 0 | Not Executed
Written By | Md. Asif Hassan |  |  |  |  | 0 | Out of Scope
Executed By | Md. Asif Hassan
Reviewed By | -
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 58 | 9 | 0 | 0 | 67
Grand Total | 58 | 9 | 0 | 0 | 67
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.
New Features | Testing Scope | Testing Environment :Google Chrome Browser

## Bug Report
Bug Reporting
# SL 01
Issue: First and last names should not start with a special character.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd/ 2. Click on the Register button at the right corner. 3. Fill all the fiels with valid credentials
4. Click 'Continue'.
Env: Production.
Module: Register
Severity: P4
Screenshot: First and last names should not start with a special character
Responsible QA: Md. Asif Hassan
Bug Reporting
# SL 02
Issue: First name and last name should not start with number.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd/ 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P5
Screenshot: First name and last name should not start with number
Responsible QA: Md. Asif Hassan
Bug Reporting
# SL 03
Issue: First name and last name should not start decimal.
Reproducing Steps:
1. Go to the URL https://www.startech.com.bd/ 2. Click on the Account button in the right corner. 3. Click the "Register" link and put data on the mentioned field.
Env: Production
Module: Login
Severity: P5
Screenshot: First name and last name should not start decimal.
Responsible QA: Md. Asif Hassan
Bug Reporting
# SL 04
Issue: A comma should not be expected between the name field.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd/ 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P6
Add text with Comma in first name and last name
Responsible QA: Md. Asif Hassan
Bug Reporting
# SL 05
Issue: Registered with invalid email address.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd/ 2. Click on the Register button at the right corner. 3. Fill all the files with valid credentials. 4. Click 'Continue'.
Env: Production.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: Invalid email address error
Expected: Should not allow registration with invalid email address.
Responsible QA: Md. Asif Hassan
Bug Reporting
# SL 06
Issue: Click on "Forgotten Password?" and Account deleted
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd/ 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P2
Screenshot: "Forgotten Password" error
Responsible QA: Md. Asif Hassan

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (50/50)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (45/50)*100 = 90%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/50)*100 = 10%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A